}

Guide 1. Definition of the APT Project

Capstone Course

- PART I

1. Personal Background

Below is a table in which you must fill in the requested information.

| Student Name | Franco Carvajal Paz |
| --- | --- |
| Tax ID | 19,393,665-2 |
| Major | Computer Engineering |
| Campus | Viña del Mar |

| Student Name | Nicolás Tapia Luque |
| --- | --- |
| Tax ID | 18.300.494-8 |
| Major | Computer Engineering |
| Campus | Viña del Mar |

| Student Name | Martín López Ovalle |
| --- | --- |
| Tax ID | 20.688.489-4 |
| Major | Computer Engineering |
| Campus | Viña del Mar |

2. APT Project Description

In the description, briefly state the name of your APT project and the competencies from the graduate profile that you will be applying. If your degree program defines performance areas, also mention which performance areas the project is linked to.

| Project Name | Predictive Maintenance at Química Latinoamericana. |
| --- | --- |
| Performance Area(s) | Analysis and Evaluation of IT Solutions. Software Development. |
| Skills | Develop a software solution using techniques that systematize the development and maintenance process, ensuring that objectives are met. Build data models to support the organization’s requirements according to a defined design that is scalable over time. Conduct certification testing of both products and processes using industry-defined best practices. |

3. APT Project Rationale

Below are various fields that you must complete with the requested information. This section asks you to describe your project in detail and justify its relevance and significance.

| Relevance of the APT Project | The purpose of this project is to develop and implement a predictive maintenance system based on machine learning models for Química Latinoamericana S.A. Its primary objective is to anticipate failures in critical industrial equipment. The initiative is justified by the strategic need to reduce unplanned downtime, optimize the useful life of assets, and raise worker safety standards. Consequently, addressing this issue will add significant value to the organization, directly impacting its economic and operational indicators. |
| --- | --- |
| APT Project Description | The project consists of designing, developing, and implementing a predictive maintenance system for the early detection and anticipation of anomalous values |
| Relevance of the Project to the Degree Program Outcomes | This project is fully aligned with the graduate profile of the computer engineering program, as it requires the development and implementation of a technological solution to address a specific problem |
| Relation to Professional Interests | This project aligns with the group’s professional interests, as it relates to the fields of machine learning and data science. This project is a great opportunity to develop our skills by addressing a real-world problem |
| Feasibility of the APT Project | The project is feasible because it is linked to internal projects at DUOC UC. The development of this project is feasible thanks to the strengths we bring as a team in the areas of machine learning, development, and project design. These skills allow us to seize the opportunity to make a real impact on the industry. At the same time, the project must address various technical and structural challenges, such as the complexity of data collection and class imbalance, and overcome the constraints of the 16-week timeframe allotted for the project’s completion. |

- PART II

4. Objectives

In this section, you must define the general and specific objectives of the APT Project. It is important to note that objectives must be stated clearly and concisely, without further explanation—that is, they must be self-explanatory. We suggest phrasing them using an infinitive verb, as this requires specifying concrete actions.

| General Objective | Develop a predictive model for the company Quimica Latinoamericana |
| --- | --- |
| Specific Objectives | - Technical requirements will be gathered and defined - The conceptual and logical architecture, as well as the data ingestion pipeline, will be designed, achieving 100% of the proposed structure - The model will be built, trained, and fine-tuned to achieve metrics of 80% or higher - The model and the operational environment will be validated, ensuring that the system generates early warnings with 80% accuracy regarding recorded events |

5. Methodology

In the following section, you must describe the methodology—specific to your discipline—that you will use to complete the APT project described above, including the stages and work methods.

Description of the Methodology

To address the development of the predictive maintenance system, we will use a hybrid methodological approach. For the predictive model’s life cycle, we will use the CRISP-DM methodology, ensuring a proper understanding of the business and the processing of data from Química Latinoamericana S.A.’s sensors. In parallel, for technical and team management, we will work under an agile framework using a kanban system supported by a schedule of objectives, and we will apply Trunk-Based Development to ensure the continuous integration of our code. The project will last 16 weeks and is divided into 3 phases - Phase 1: Kickoff (August 17, 2026, to September 6, 2026) - Phase 2: Development (September 10, 2026, to October 29, 2026) - Phase 3: Closure (November 2, 2026, to November 8, 2026) Roles and Responsibilities: - Franco Carvajal (Machine Learning Lead) Responsible for leading the CRISP-DM cycle - Nicolas Tapia (Data and Backend Engineer) Responsible for designing the architecture and deploying the database - Martin Lopez (Front-End/Integration Developer) Responsible for creating the graphical user interface (GUI) and connecting the alert module to the database To manage the data from Quimica Latinoamerica S.A.’s IoT sensors, the strategy is to implement a data pipeline using AWS services and PostgreSQL

6. Deliverables

Below, describe what deliverables will be evaluated in the progress report and the final report for your APT project. These deliverables must be agreed upon with your instructor. Deliverables are defined as the outputs developed during the project that serve to demonstrate or document how the work has been implemented.

| Type of Evidence (progress or final) | Name of Evidence | Description | Justification |
| --- | --- | --- | --- |
| Preliminary | Architecture Documentation | Technical diagram of the architecture and data processing pipelines | Enables validation of Phase 2 project execution |
| Preliminary | Predictive Model | File and notebook containing the source code for the machine learning model | Evidence of compliance with the core project requirements |
| Final | Minimum Viable Product (MVP) | Deployed functional prototype that includes the dashboard and the automated alert system | This is the main deliverable |

7. Work Plan

In the table below, define the schedule for your APT Project as required.

| APT Project Work Plan |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Competency or competency units | Name of Activities/Tasks | Description of Activities/Tasks | Resources | Duration of the Activity | Person in Charge | Notes |
| Building Data Models | Phase 1: Architecture Assessment and Design | Definition of technical requirements, success metrics, and logical architecture design | Technical Documentation | 3 weeks (S1 - S3) | Nicolas Tapia | It is crucial that Química Latinoamericana S.A. be available to define the variables and machines to be used |
| Build a data model | Phase 2: Database and AI model implementation | Set up AWS environments, create the database, perform exploratory data analysis (EDA), and train the algorithms | AWS services, Python, and open-source libraries | 5 weeks (S4–S8) | Franco Carvajal | Mitigating class imbalance, data acquisition, and model training time |
| Develop a software solution | Phase 2: Front-end development, dashboard, and alert system | Creating the graphical interface, integrating database and model usage, and creating the alert system | Open-source frameworks | 5 weeks (S9–S13) | Martin Lopez | Focus on system usability and data consumption |
| Testing | Phase 3: Validation, testing, and MVP completion | Generating tests in the environment, making final adjustments | Test environment deployed | 3 weeks (S14–S16) | Full team Franco Carvajal, Nicolas Tapia, Martin Lopez | The milestones for this phase must be met in advance |

8. Gantt Chart

Find a Gantt chart format that works for you and use it to organize the activities planned in the previous section, taking into account the time allocated for the development of your APT Project. You must adhere to the academic calendar when carrying out the three phases outlined in the Degree Portfolio course.

You may modify the schedule

| Activity | Phase 1 |  |  |  | Phase 2 |  |  |  |  |  |  |  |  |  |  |  | Phase 3 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | S 1 | S 2 | S 3 | S 4 | S 5 | S 6 | S 7 | S 8 | S 9 | S 10 | S 11 | S 12 | S 13 | S 14 | S 15 | S 16 |  | S 17 | S 18 |
| Requirement Gathering and Articles of Incorporation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Definition of Metrics and Architecture Design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environment assessment and database creation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Data collection and exploratory analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Model creation and training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Graphical interface creation and dashboard development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Database integration and alert module development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Test generation and accuracy evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Final adjustments to the MVP and final report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project delivery |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

If the APT Project is a group project, please list the names of the individuals responsible for each task or activity in this column. This will allow for separate evaluations of each group member.